## 2021-2022
The National Priorities of EITI Armenia
1. Deepening the implementation of EITI transparency and accountability Standard in the mining sector, addressing the identified gaps 2. Development of institutional capacities of the stakeholders of the sector, introduction of systematic disclosures, building capacity for using and analyzing disclosed data 3. Ensuring awareness about the mining sector 4. Enhancing the culture of responsible mining through application of the best international practices and improving legal regulations 5 Enhancing competitive investment environment for responsible investors
2021-2022 EITI WORK PLAN OF ARMENIA
Objective | Rationale: Governance-related challenges and obstacles in the mining sector | EITI Standard requirement | No. | Activity | Outcome/Output | Responsible Party(s) | Timeline | 2021-2022 Planned Costs, USD | Funding Source | Risk assessment (low(L), moderate(M), high(H))
Ensuring accessible and timely information | Lack or non-systemic character of the accessible, up-to-date, full and user-friendly information at the primary sources
|  | 7.2 | 1 | Posting up-to-date information/data on the EITI Armenia website | Reports, progress reports, video-clips, publications, legal acts, news items | MSG, Arm-EITI Secretariat | 2021 2022 |  | State Budget | L
|  | 7.2 | 2 | Maintenance of the EITI Armenia website, upgrade of the EITI online reporting platform | Operational website and online reporting platform | Arm-EITI Secretariat/PM's Office, EKENG, selected company | 2021 2022 |  | State Budget | L
|  | 7.1 | 3 | Publication of user friendly information/data on the mining sector and EITI Armenia, preparation of public service announcements (PSAs) | Information sheets, infograms, EITI quarterly and annual progress reports, EITI report, EITI brief report, informative video-clips | MSG, Arm-EITI Secretariat/PM's Office | 2021 2022 | 20000 | World Bank, State Budget, donors | L
|  | 7.1 | 4 | Public awareness and coverage of the EITI processes and recorded results (through social media, mass media, TV broadcasts) | Information on the mining sector and EITI broadcasted and published by social media | MSG, Arm-EITI Secretariat/PM's Office | 2021 2022 |  |  | L
|  | 7.1 | 5 | Revision of Armenia EITI Armenia Communication Strategy and Action Plan | Revised Communication Strategy and Action Plan, re-branding | MSG, Arm-EITI Secretariat/PM's Office | Q3, Q4, 2021 Q1, 2022 | 5000 | State Budget, donors | M
|  | 7.2 | 6 | Consultations on the online submission of EITI public reports | Reports published on the EITI Armenia online reporting platform | Arm-EITI Secretariat/PM's Office | 2021 2022 |  | State Budget | L
|  | 7.1 | 7 | Implementation of awareness raising activities, working meetings with stakeholders | Meetings, including with regional and community stakeholders, educational institutions and the general public | MSG, Arm-EITI Secretariat/PM's Office | 2021 2022 | 25000 | World Bank, State Budget, donors | L
|  | 7.1 | 8 | Official presentation of the 3rd EITI report for 2019 FY / EITI conference | EITI Conference (on site or online) | MSG, Arm-EITI Secretariat/PM's Office | Q2, 2021 | 6200 | World Bank, State Budget | M
|  | 7.1 | 9 | Official presentation of the 4th EITI report for 2020 FY / EITI conference | EITI Conference | MSG, Arm-EITI Secretariat/PM's Office | Q2, 2022 | 5000 | World Bank, State Budget | L
|  |  | 10 | Participation in the EITI Global Conference | Meetings with representatives of partner countries, officials from the EITI International Secretariat, Board, cooperation agreements | MSG, Arm-EITI Secretariat/PM's Office | 2022 | 5000 | World Bank, State Budget | M
|  | 7.2 | 11 | In the scope of “Improvement of Transparency and Accountability in the Mining Sector & Promotion of EITI” (ITAMSPE) USAID grant project production and dissemination of educational videos on EITI and mining sector in Armenia | • Environmental and social monitoring manual for public oversight; • Online mining information platform; • Study of non-operating mining companies' liabilities; • Investigative materials / videos, articles / | Transparency International Anticorruption Center (TIAC) Armenia, AUA Center for Responsible Mining , EcoLur NGO, investigative journalists NGO | Q2, Q3, 2021 |  | USAID Armenia/TIAC Armenia
|  |  | 12 | In the scope of ITAMSPE USAID grant project raising public awareness on mining and EITI /discussions particularly in affected communities | Training on EITI for CSOs, discussions with skakeholder groups and representatives of affected communities | Transparency International Anticorruption Center (TIAC) Armenia, AUA Center for Responsible Mining , EcoLur NGO | Q2, Q3, 2021 |  | USAID Armenia/TIAC Armenia
Increasing public accountability and oversight, reducing corruption risks
Maintaining Armenia EITI membership status | Decreased interest among the EITI implementation stakeholders
|  | 7.3 7.4 | 13 | Development of a roadmap for the elimination of legal and procedural gaps in the metal mining sector, recorded in the EITI 1st և 2nd reports | draft Roadmap |  | Q1, Q2, 2021 |  | State Budget | L
|  |  | 14 | Approval of the Roadmap by the MSG | Roadmap | MSG, Arm-EITI Secretariat/PM's Office | Q2, 2021 |  |  | L
|  |  | 15 | Establishment of MSG working groups to address gaps recorded in the Roadmap | MSG working groups | MSG, Arm-EITI Secretariat/PM's Office, State Agencies | Q2, 2021 |  |  | L
|  |  | 16 | Works on roadmap gaps elimination by working groups | Working groups meetings, discussions, recommendations, draft legal acts | MSG working groups, State Agencies, Arm-EITI Secretariat/PM's Office | Q2, Q3, Q4 - 2021 2022 |  | State Budget | L
|  | 1.4 | 17 | Holding MSG meetings | MSG meetings | MSG, Arm-EITI Secretariat/PM's Office | Q2, Q3, Q4 - 2021 Q1, Q2, Q3, Q4 - 2022 |  | State Budget | L
|  | 1.4 | 18 | Holding MSG working group meetings | Meetings | MSG working groups, Arm-EITI Secretariat/PM's Office, | 2021 2022 |  | State Budget | L
|  | 1.4 | 19 | Nomination of the MSG new members and approval of the MSG composition | RA Prime Minister Decree, MSG | MSG constituencies, Arm-EITI Secretariat/PM's Office | 2021 Q4, 2022 |  |  | L/M
|  | 1.4.b | 20 | Amendments to the MSG ToRs (as needed) | MSG ToRs | MSG, Arm-EITI Secretariat/PM's Office | 2021 2022 |  |  | L/M
|  |  | 21 | Participation in EITI Board meetings and conferences | EITI Board meetings | MSG, Arm-EITI Secretariat/PM's Office | 2021 2022 | 4000 | World Bank, State Budget, donors | M/H
|  | 1.5 | 22 | Development and approval of Armenia's 2020 EITI Work plan implementation report | EITI Armenia 2020 Work Plan implementation report | MSG, Arm-EITI Secretariat/PM's Office | Q2, 2021 |  | State Budget | L
|  | 1.5 | 23 | Development and approval of Armenia's 2021-2022 EITI Work plan | EITI Armenia 2021-2022 Work Plan | MSG, Arm-EITI Secretariat/PM's Office | Q1, Q2, 2021 |  | State Budget | L
|  |  | 24 | Collaboration with partner and donor organisations | Meetings with donors and partners | MSG, Arm-EITI Secretariat/PM's Office | 2021 2022 |  |  | L
|  |  | 25 | Operation of the EITI Armenia Secretariat | EITI implementation documents, reports, work plans, organisation of meetings, support to MSG, local and international cooperation activities, provision of consultancy, State budget documents, reports, ensuring of procurement procedures | Arm-EITI Secretariat/PM's Office | 2021 2022 | 50000 | State Budget | L
|  | 1.4 7.4 | 26 | Preparation of EITI Armenia 2020 Annual Progress Report and approval by the MSG | EITI Armenia 2020 Annual Progress Report | MSG, Arm-EITI Secretariat/PM's Office | Q2 - 2021 |  | State Budget | L
|  | 1.4 7.4 | 27 | Preparation of EITI Armenia Quarterly Progress Reports and approval by the MSG | Quarterly progress reports | MSG, Arm-EITI Secretariat/PM's Office | Q1, Q2, Q3, Q4, 2021 Q1, Q2, Q3, Q4, 2022 |  |  | L
|  | 1.4 | 28 | Cooperation with the EITI International Secretariat and EITI member countries | Correspondence, meetings, conference calls, online discussions | MSG, Arm-EITI Secretariat/PM's Office | 2021 2022 |  |  | L
|  |  | 29 | Payment of EITI membership contribution |  | MSG, Arm-EITI Secretariat/PM's Office | Q3, 2021 Q3, 2022 | 20000 | State Budget | L
Preparation of the EITI Reports in accordance with the EITI Standard
|  | 4.8 | 30 | Preparation of the 3rd EITI Armenia Report for 2019 FY | EITI draft Report, EITI Report of Armenia, Summary data template | Independent Administrator, MSG, Arm-EITI Secretariat/PM's Office | Q4, 2020 - Q2, Q3, 2021 | 93500 | World Bank, State Budget | L
|  | 7.3 7.4 | 31 | Discussion of the recommendations, discrepancies and gaps registered in the 2019 EITI Report (Including recommendations by the EITI International Secretariat) by the MSG aiming at determination of ways to implement the recommendations and to eliminate discrepancies. | Meetings, discussions, recommendations, draft legal acts, MSG meetings | MSG, Arm-EITI Secretariat/PM's Office, State agencies | Q3, Q4, 2021 |  | State Budget | M
|  | 7.2 7.3 | 32 | Implementation of legislative amendments in case of a positive decision by the MSG to extend the EITI Standard on the mineral water extraction and processing of natural metal resources sectors (according to the Scoping study recommendations), as well as for implementation systematic disclosures | Meetings, discussions, draft legal acts | MSG, State Agencies, Arm-EITI Secretariat/PM's Office | Q3, Q4, 2021 Q1, Q2, Q3, Q4, 2022 | 15000 | World Bank, State Budget | M
|  | 4.8 7.2 | 33 | Amendments to the RA Government decree N 666, approval of the amendments by the MSG and submission of the draft decree to the Government of Armenia (as needed) | RA Government Decree | MSG, Arm-EITI Secretariat/PM's Office | Q1, 2022 |  | State Budget | L
|  | 7.2 7.3 | 34 | Preparation of the ToRs for the Independent Administrator for the 4th EITI Armenia Report (considering transitional recommendations from the EITI International Secretariat) and approval by the MSG | IA draft ToRs | MSG, Arm-EITI Secretariat/PM's Office | Q3, 2021 |  | State Budget | L
|  |  | 35 | Selection of the Independent Administrator (Tender and approval) | Tender announcement for Independent Administrator, tender, contract awarded to the Independent Administrator | MSG, Arm-EITI Secretariat/PM's Office | Q3, Q4, 2021 |  |  | L
|  | 4.8 | 36 | Preparation of the 4th EITI Armenia Report for 2020 FY | EITI draft Report, EITI Report of Armenia, Summary data template | Independent Administrator, MSG, Arm-EITI Secretariat/PM's Office | Q4, 2021 - Q2, 2022 | 84000 | World Bank, State Budget | L
|  | 7.3 7.4 | 37 | Discussion of the recommendations, discrepancies and gaps registered in the 2020 EITI Report (Including recommendations by the EITI International Secretariat) by the MSG aiming at determination of ways to implement the recommendations and to eliminate discrepancies. | Meetings, discussions, recommendations, draft legal acts, MSG meetings | MSG, Arm-EITI Secretariat/PM's Office, State agencies | Q3, Q4, 2022 |  | State Budget | M
|  | 7.2 7.3 | 38 | Preparation of the ToRs for the Independent Administrator for the 5th EITI Armenia Report (considering transitional recommendations from the EITI International Secretariat) and approval by the MSG | ToRs | MSG, Arm-EITI Secretariat/PM's Office | Q3, 2022 |  | State Budget | L
|  |  | 39 | Selection of the Independent Administrator (Tender and approval) | Tender announcement for Independent Administrator, tender, contract awarded to the Independent Administrator | MSG, Arm-EITI Secretariat/PM's Office | Q3, Q4, 2022 |  |  | L
|  | 4.8 | 40 | Preparation of the 5th EITI Armenia Report for 2021 FY | EITI Armenia Report | Independent Administrator, MSG, Arm-EITI Secretariat/PM's Office | Q4, 2022 - Q2, 2023 | 60000 | World Bank, State Budget | L
Launching an online public Beneficial Ownership Register, ensuring access to information on beneficial owners, increasing opportunities for public oversight
|  | 7.1 | 41 | Public awareness event for launching the public Beneficial Ownership Register | Press Conference/event | MSG, Arm-EITI Secretariat/PM's Office | Q2, 2021 | see act. 8 | World Bank, State Budget | L
|  | 2.5 | 42 | Training / consulting on filling in and submitting Beneficial Owners declarations on the online register platform | Training/consultancy, BO declarations published on Register | Arm-EITI Secretariat/PM's Office, State Agencies, selected company | 2021 2022 |  | State Budget | L
|  |  | 43 | Development of legal acts drafs improving the process of beneficial ownership disclosures | Draft legal acts | MSG BO working group, Ministry of Justice, MSG, Arm-EITI Secretariat/PM's Office | 2021 2022 |  | State Budget | L
|  |  | 44 | Approval of the BO legal acts drafts by the MSG and submission to the Government of Armenia | Draft legal acts | MSG, Arm-EITI Secretariat/PM's Office, Ministry of Justice | 2021 2022 |  | State Budget | L
|  |  | 45 | Monitoring of BO data published on the public online register, quantitative analysis, qualitative assessment (as needed), as well as analysis of the strengths and weaknesses of the process of submitting BO declarations | Discussions, opinions, analysis, draft legal acts | Arm-EITI Secretariat/PM's Office, State agencies, MSG BO working group | 2021 2022 |  | State Budget | L
|  |  | 46 | Addressing of the recommendations presented by the EITI International Secretariat in the BO 2.5 Requirement Validation Assessment Report | Discussions, meetings, opinions, analysis, supporting information collected, draft legal acts (as needed) | Arm-EITI Secretariat/PM's Office, State agencies, MSG BO working group | Q2, Q3, Q4 - 2021 |  | State Budget | L
|  |  | 47 | Upgrading of the public Beneficial Ownership Register (as needed) | Upgraded online Register, eliminations of bugs on BO declaration submission software | Arm-EITI Secretariat/PM's Office, State agencies, selected company | 2021 2022 |  | State Budget, donors | L
Expansion of the scope of the EITI in Armenia, in case of the MSG decision on the extension of the scope of implementation of the EITI Standard, harmonization of the legal framework
|  |  | 48 | Preparation of a Scoping Study by the Independent Administrator on Expanding the scope of the EITI Armenia | Scoping Study, MSG decision | MSG, Arm-EITI Secretariat/PM's Office, Independent Administrator | Q2, Q3 , 2021 |  | World Bank, State Budget | L
|  | 7.3 | 49 | Discussion of the Scoping Study by the MSG, making a decision on the expediency of expanding the scope of EITI Armenia | Meetings, discussions, opinions, MSG decisions | MSG, Arm-EITI Secretariat/PM's Office, Independent Administrator | Q2, Q3, 2021 |  |  | M
|  |  | 50 | In case of a positive decision of the MSG on the expansion of the scope of the EITI Armenia, discussions with the stakeholders (representatives of companies, government agencies, etc.) | Meetings, discussions | MSG, Arm-EITI Secretariat/PM's Office, State agencies, MSG working group | Q3, Q4, 2021 |  | State Budget | M
|  | 7.3 | 51 | Drafting legal acts based on the recommendations of the Scoping study and held discussions, approval of the draft legal acts by the MSG | Draft legal acts | MSG, Arm-EITI Secretariat/PM's Office, State agencies | Q4, 2021 Q1, 2022 |  | State Budget | M
|  |  | 52 | Circulation of draft legal acts and submission to the Government of the Republic of Armenia for adoption | Draft legal acts | MSG, Arm-EITI Secretariat/PM's Office, State agencies | Q1, Q2,Q3, 2022 |  | State Budget | M
Ensuring systematic disclosures of EITI data, strengthening the capacity of the MSG and stakeholders | Lack of legal, institutional and technical capacity to carry out systematic disclosures
|  | 4.8/4.9 | 53 | Development and approval of a ToRs for the study of the legal, institutional and technical possibilities for the systematic data disclosures (including the possibility of conducting regular publications of open data on automated data generation portal / EITI official website / and websites of relevant government agencies) | ToRs | MSG, Arm-EITI Secretariat/PM's Office | Q1, Q2, 2021 |  | State Budget | M/H
|  |  | 54 | Selection of the Consultant for the Study | Contract | MSG, Arm-EITI Secretariat/PM's Office | Q2, 2021 |  | World Bank, State Budget | M
|  |  | 55 | Preparation of the study and submission for MSG's approval | Study paper | Selected company, MSG, Arm-EITI Secretariat/PM's Office | Q2, Q3, 2021 | 9000 | World Bank, State Budget | M
|  |  | 56 | According to the recommendations of the study, preparation of the ToRs for development of software package for routine data disclosures on systematic disclosures' portal and in-line state agencies' websites | ToRs | MSG, Arm-EITI Secretariat/PM's Office | Q4, 2021 |  | State Budget | L
|  |  | 57 | Approval of ToRs by the MSG | ToRs | MSG, Arm-EITI Secretariat/PM's Office | Q4, 2021 |  | State Budget | L
|  |  | 58 | Selection of company (s) for systematic disclosures software package development | Tender, selections of the company(s), contract(s) | MSG, Arm-EITI Secretariat/PM's Office, Selected company(s) | Q1, Q2, 2022 |  | State Budget | L
|  |  | 59 | Development of a software package that allows routine data publications (disclosures) based on the open data principle on the websites of the in-line state agencies. | Software package | Selected company(s), MSG, Arm-EITI Secretariat/PM's Office | 2021-2024 | 150000 | World Bank, State Budget | M
|  |  | 60 | Introduction of systematic data disclosures through new software (portal and in-line state agencies websites) | Systematic disclosures | State agencies, Arm-EITI Secretariat/PM's Office, | Q4 - 2022-2024 |  | State Budget | L
|  |  | 61 | Capacity building activities for the Audit Chamber of Armenia | meetings, training | Arm-EITI Secretariat/PM's Office, Consultant company | 2021 2022 | 50000 | World Bank, State Budget | L
|  |  | 62 | Capacity building activities for the Parliament representatives | meetings, training | Arm-EITI Secretariat/PM's Office, Consultant company | 2021 2022 |  | World Bank, State Budget | L
|  |  | 63 | Capacity building activities for the representatives of State agencies | meetings, training | Arm-EITI Secretariat/PM's Office, Consultant company | 2021 2022 |  | World Bank, State Budget | L
|  |  | 64 | Capacity building activities for the affected communities' representatives to develop effective participation, sustainable development programs and policy preparation skills | meetings, training | Arm-EITI Secretariat/PM's Office, Consultant company | 2021 2022 |  | World Bank, State Budget | L
|  |  | 65 | Mining and EITI data analytical capacity building activities for CSOs և Media representatives | meetings, training | Arm-EITI Secretariat/PM's Office, Consultant company | 2021 2022 |  | World Bank, State Budget | L
|  |  | 66 | Conducting competitions of thematic research by the students-researchers of educational institutions, public discussion of the winning papers, awarding the winners, publication of papers | Paper awards event, published papers | Arm-EITI Secretariat/PM's Office | 2021 2022 | 12000 | World Bank, State Budget, donors | L
|  |  | 67 | EITI data analysis heckathon | Heckathon |  | Q4, 2021 |  | "World Bank, State Budget, donors" |  | preliminary
Implementation of responsible mining practices | Lack of responsible mining culture, deficiency of relevant legal framework, insufficient capacity of relevant state agencies, mining companies and civil society
|  | 7.4 | 68 | Implementation of roadmap activities to support the introduction of responsible mining practices | Roadmap activities | MSG, Arm-EITI Secretariat/PM's Office, MSG working group, State agencies | 2021 2022 |  | State Budget, donors | M
|  |  | 69 | Holding meetings of the working group in support of the introduction of responsible mining practices, presentation of the recommendations, proposals for legislative amendments | Meetings, recommendations, draft legal acts | MSG, Arm-EITI Secretariat/PM's Office, MSG working group, State agencies | 2021 2022 |  | State Budget, donors | L
|  |  | 70 | Participation in the mining strategy development works | BO working group meetings, recommendations, opinions | MSG, Arm-EITI Secretariat/PM's Office, MSG working group, State agencies | Q2, Q3, Q4 , 2021 Q1, Q2, 2022 |  | State Budget | L
|  |  | 71 | Revision of the RoadMap on introduction of responsible mining practices | Revised Roadmap | MSG working group, Arm-EITI Secretariat/PM's Office | Q2, 2021, Q2, 2022 |  | State Budget | L
STATUS OF ACTIVITIES
Completed
Open
Ongoing