## Sheet1
2019-2020 EITI WORK PLAN OF ARMENIA
Objective | Rationale: Governance-related challenges and obstacles in the sector | EITI Standard requirement | No. | Activity | Outcome/Output | Responsible Party | Timeline | Cost, USD | Funding Source
Ensuring accessible and timely information | Availability of accessible, timely and comprehensive information on the mining sector and EITI
|  | 7.2 | 1 | Further improvement of the ARM-EITI official website | Improved ARM-EITI website, equipped with tools that make the data accessible in a user-friendly manner and relevant to the Open Data Principle. | RA Prime Minister's Staff/ARM-EITI Secretariat, selected organization | Q1, Q2, Q3, Q4, 2019 Q1, Q2, Q3, Q4, 2020 | see activity N3 | World Bank
|  | 7.2 | 2 | Development of a ToR for online reporting platform improvement and approval of the ToR by MSG | ToR | RA Prime Minister's Staff/ARM-EITI Secretariat, MSG | Q1, 2019 | 1000 | State Budget
|  | 7.2 | 3 | Development of improved online reporting platform | contract with selected organization, databases, database processing tools, more user-friendly, improved online reporting platform | RA Prime Minister's Staff/ARM-EITI Secretariat, selected organization | Q1, Q2, 2019 | 6000 | World Bank
|  |  | 4 | Ongoing website support |  | Selected organization, RA Prime Minister's Staff/ARM-EITI Secretariat | Q1, Q2, Q3, Q4, 2019 Q1, Q2, Q3, Q4, 2020 | Finding for 2019 is included in the 2nd activity funding of 2018 EITI Work plan | UNDP, donors
|  | 7.1 | 5 | Posting timely information on the EITI website (reports, videos, protocols) | Reports, videos, legal acts, news items uploaded on the website | RA Prime Minister's Staff/ARM-EITI Secretariat, MSG | Q1, Q2, Q3, Q4, 2019 Q1, Q2, Q3, Q4, 2020 |  | State Budget
|  | 7.1 | 6 | Disclosure and publication of information on the mining sector and EITI in an easily understood language, preparation of social advertising | Information sheets, infograms, EITI quarterly and annual progress reports, EITI report, EITI brief report, informative video-clips | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat | Q1, Q2, Q3, Q4, 2019 Q1, Q2, Q3, Q4, 2020 | 7500 | World Bank, donors
|  | 7.1 | 7 | Public awareness campaign on mining sector and EITI and their elucidation via social media (YouTube, Twitter, Facebook, etc.) | Information about mining and EITI published on social media | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat | Q1, Q2, Q3, Q4, 2019 Q1, Q2, Q3, Q4, 2020
|  | 7.1 | 8 | Implementation of awareness raising activities, working meetings with stakeholders | Meetings, including with representatives of affected communities, meetings with educational institutions, meetings with wider constituencies | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat | Q1, Q2, Q3, Q4, 2019 Q1, Q2, Q3, Q4, 2020 | 10000 | World Bank, State Budget, donors
|  | 7.1 | 9 | Official presentation of the EITI first report / EITI conference, EITI website launch, presentation of online reporting platform and database | EITI Conference | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat | Jan, 2019 | 7500 | World Bank, State Budget, GIZ
|  | 7.1 | 10 | Official presentation of the EITI second report / EITI conference, presentation of the BO public register | EITI Conference | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat | Q1, 2020 | 7500 | World Bank, State Budget, donors
|  | 7.2. b) | 11 | In the scope of “Improvement of Transparency and Accountability in the Mining Sector & Promotion of EITI” (ITAMSPE) USAID grant project production and dissemination of educational videos on EITI and mining sector in Armenia | Educational videos on EITI and mining sector in Armenia | Transparency International Anticorruption Center (TIAC) Armenia, AUA Center for Responsible Mining | Q1, Q2, 2019 | 20000 | USAID Armenia/TIAC Armenia
|  |  | 12 | In the scope of ITAMSPE USAID grant project raising public awareness on mining and EITI /discussions particularly in affected communities | Training modules on EITI for MSG, CSOs, community youth clubs (CYCs), local groups and activists and organization of trainings on EITI for MSG, CSOs, local groups and activists | Transparency International Anticorruption Center (TIAC) Armenia, AUA Center for Responsible Mining | Q1, Q2, 2019 | 17700 | USAID Armenia/TIAC Armenia
Increased accountability and public oversight, reduction of corruption risks
Development of the public register for disclosure of beneficial owners and publication of information on ulltimate beneficial owners
|  | 7.1 | 13 | Organization of an outreach event on BO disclosure process, legal regulations and launch of the process of the BO public disclosure | Press conference | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat | Q1, Q4, 2019 | 2500 | World Bank
|  | 2.5 | 14 | Training on the international experience of development of declaration forms on BOs and submission of declarations | Training | RA Prime Minister's Staff/ARM-EITI Secretariat, MSG | Q1, 2019 | 10000 | World Bank, State Budget
|  |  | 15 | Development of sub-legal acts for disclosure of BOs | Draft legal acts | BO inter-agency task force, Ministry of Justice, MSG, RA Prime Minister's Staff/ARM-EITI Secretariat | Q1, Q2, 2019 |  | State Budget
|  |  | 16 | Approval of draft sub-legal acts by MSG, and submission of circulated legal package to the Government | Draft legal acts | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat, relevant ministry | Q2, 2019 |  | State Budget
|  |  | 17 | Preparation and approval of a ToR for development of a public register of BO disclosure | ToR | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat, Ministry of Justice | Q2, 2019 |  | State Budget
|  |  | 18 | Election of the organization for development of a public register for BO disclosure and development works of the register | Public register | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat, relevant state bodies, selected organization | Q2, Q3, Q4, 2019 | 15000 | World Bank
|  |  | 19 | Training on filling in and submitting BO disclosure declarations | Training | RA Prime Minister's Staff/ARM-EITI Secretariat, relevant state bodies, selected organization | Q4, 2019 | 2000 | donors
|  |  | 20 | Submission of BO disclosure declarations by the companies | Declarations | Companies, State Register of the Legal Entities | Q4, 2019 Q1, Q2, Q3, Q4 2020
|  |  | 21 | Study of BO disclosure public register and disclosure process, identification of shortcomings (if necessary) | Discussions, opinions, analysis | RA Prime Minister's Staff/ARM-EITI Secretariat, relevant state body | Q1, Q2, 2020 |  | donors
|  |  | 22 | Improvement of the BO disclosure public register (if necessary) | Improved register | RA Prime Minister's Staff/ARM-EITI Secretariat, relevant state body, selected organization | Q3, Q4, 2020 |  | donors
Ensuring Armenia's EITI candidacy/membership status
|  | 8.3 | 23 | Preliminary verification of the preparedness for the EITI validation process and identification of gaps | Pre-validation checklists | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat | Q2, 2019
|  | 8.3 | 24 | Validation process | Validation | MSG working group, RA Prime Minister's Staff/ARM-EITI Secretariat, EITI International Secretariat, validators | Sept. 2019 Q2, Q3, 2019 | 4000 | World Bank
|  |  | 25 | MSG meetings | MSG meetings | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat | Q1, Q2, Q3, Q4, 2019 Q1, Q2, Q3, Q4, 2020
|  |  | 26 | MSG working group meetings | Meetings, discussions | MSG working groups, RA Prime Minister's Staff/ARM-EITI Secretariat | Q1, Q2, Q3, Q4, 2019 Q1, Q2, Q3, Q4, 2020 |  | State Budget
|  | 1.4 | 27 | Nomination of new MSG members, approval of the composition of MSG | Prime Minister’s Decree, MSG | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat | Q3, Q4, 2019
|  | 1.4.b | 28 | Review of MSG ToR (if necessary) | MSG ToR | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat | Q4, 2019
|  |  | 29 | Participation in EITI Board meetings and conferences | EITI Board meetings | MSG constituencies, MSG, RA Prime Minister's Staff/ARM-EITI Secretariat |  | 10000 | World Bank
|  | 1.5 1.4.b.iv. | 30 | Preparation of the implementation document of the 2018 EITI Work Plan of Armenia and its approval by MSG | Implementation document of the 2018 EITI Work Plan | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat | Q1, 2019
|  | 1.5 1.4.b.iv. | 31 | Preparation of the implementation document of the 2019 EITI Work Plan of Armenia and its approval by MSG | Implementation document of the 2019 EITI Work Plan | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat | Q1, 2020
|  | 1.5 1.4.b.iv. | 32 | Preparation of reviewed 2020 EITI Work Plan and its approval by MSG | Reviewed 2020 EITI Work Plan | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat | Q1, 2020
|  | 1.5 1.4.b.iv. | 33 | Development of 2021-2020 EITI Work Plan of Armenia and its approval by MSG | 2021-2020 EITI Work Plan | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat | Q4, 2020
|  |  | 34 | Collaboration with donors and partners | Meetings with donor and partner organizations | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat | Q1, Q2, Q3, Q4, 2019 Q1, Q2, Q3, Q4, 2020
|  |  | 35 | Operation of the EITI secretariat of Armenia | Works on State Budget processes, preparation of reports, coordination of projects, conduction of procurement processes | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat | Q1, Q2, Q3, Q4, 2019 Q1, Q2, Q3, Q4, 2020 | 72000 | State Budget
|  | 1.4.b.iv. 7.4 | 36 | Preparation of EITI 2018 Annual Report and its approval by MSG | EITI 2018 Annual Report | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat | Q2, 2019
|  | 1.4.b.iv. 7.4 | 37 | Preparation of EITI 2019 Annual Report and its approval by MSG | EITI 2019 Annual Report | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat | Q2, 2020
|  | 1.4.b.iv. 7.4 | 38 | Preparation of EITI quarterly progress reports and approval of reports by MSG | EITI quarterly progress reports | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat | Q1, Q2, Q3, Q4, 2019 Q1, Q2, Q3, Q4, 2020
|  | 1.4 | 39 | Collaboration with the EITI International Secretariat and other EITI member countries | Correspondence, meetings, conference calls | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat | Q1, Q2, Q3, Q4, 2019 Q1, Q2, Q3, Q4, 2020
|  |  | 40 | Payment of EITI membership fee |  | RA Prime Minister's Staff/ARM-EITI Secretariat | Q2, 2019 Q2, 2020 | 20000 | State Budget
|  |  | 41 | Translation works |  |  | Q1, Q2, Q3, Q4, 2019 Q1, Q2, Q3, Q4, 2020 | 6000 | World Bank, donors
Comprehensive EITI report consistent with the EITI Standard
|  | 7.2 | 42 | Drafting amendments to the Government Decision N666 of June 8, approval of the draft legal act by MSG and submission to the Government of Armenia | Government decision | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat | Q1, Q2 2019
|  | 7.3 | 43 | Discussion of recommendations, revealed deficiencies, and the gaps presented by the International Secretariat about the EITI 2018 Report of Armenia for the purpose of determining the implementation mechanisms of the recommendations and eliminating the causes of discrepancies | Meeting, recommendations | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat, stakeholder bodies | Q1, 2019
|  | 1.4.b.iv. | 44 | Preparation of the draft ToR of Independent Administrator for preparation of the EITI 2019 Report and approval by MSG | ToR of Independent Administrator | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat | Q2, 2019 (April, 2019) |  | State Budget
|  | 1.4.b.iv. | 45 | Elections of the Independent Administrator (tender and approval) | Tender announcement for Independent Administrator, tender, contract with IA | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat | Q2, 2019
|  | 4.8 8.2 | 46 | Preparation of the 2019 EITI Report of Armenia | EITI 2019 Report | Independent Administrator, MSG, RA Prime Minister's Staff/ARM-EITI Secretariat | Q2, Q3, Q4, 2019 | 80000 | World Bank
|  | 1.4.b.iv. | 47 | Preparation of the draft ToR of the Scoping Study of the EITI 2020 Report and approval by MSG (if necessary) | ToR | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat | Q4, 2019- Q1, 2020 |  | GIZ
|  | 1.4.b.iv. | 48 | Preparation of the Scoping Study of the EITI 2020 Report (if necessary) and draft ToR of Independent Administrator for preparation of the EITI 2020 Report | Contract with selected organization, scoping study, draft ToR of IA for preparation of the EITI 2020 Report | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat, selected organization | Q4, 2019- Q1, 2020 | 5000 | World Bank
|  | 1.4.b.iv. | 49 | Approval of the ToR of Independent Administrator for preparation of the EITI 2020 Report and election of IA | ToR of IA for preparation of the EITI 2020 Report, contract with IA | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat | Q2, 2020
|  | 4.8 8.2 | 50 | Preparation of the 2020 EITI Report of Armenia | EITI 2020 Report | IA, MSG, RA Prime Minister's Staff/ARM-EITI Secretariat | Q2, Q3, Q4, 2020 | 80000 | donors
Expanding the scope of the EITI Armenia, study of the Armenian legal framework, disclosure of inconsistencies and gaps with the EITI Standard | Alignment of the Armenian legal framework for the purpose of expanding the EITI scope
|  |  | 51 | Preparation of a ToR for a study on expanding the scope of EITI in Armenia and respective legal gaps, and scoping, and approval of ToR by MSG | MSG decision on expanding the scope of the EITI Armenia, ToR | RA Prime Minister's Staff/ARM-EITI Secretariat, MSG | Q1, Q2, 2019 | 1000 | State Budget
|  | 7.3 | 52 | Preparation of a study on expansion of the scope of EITI in Armenia and identification respective legal gaps, and scoping. | Scoping Study, draft legal acts | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat, selected organization, MSG working group | Q1, Q2, Q3, 2019 | 10000 | World Bank
|  |  | 53 | Stakeholder discussions on expanding the scope of the EITI Armenia (companies, state agencies, and other stakeholders) | Meetings, discussions | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat, State agency, selected organization, MSG working group | Q2, Q3, 2019 | 2000 | World Bank
|  | 7.3 | 54 | Approval of the Study and draft legal acts by the MSG and submission of the circulated draft legal acts to the Government | Draft legal acts | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat, relevant ministry | Q3, Q4, 2019 Q1, 2020 |  | State Budget
Implementation of responsible mining practices in Armenia according to the RM roadmap and in line with best international experience | Implementation of responsible mining practices in Armenia
|  | 8.3.a.iii. | 55 | Implementing roadmap activities to support introduction of responsible mining practices | Activities of the Roadmap | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat, MSG working group, state bodies | Q1, Q2, Q3, Q4, 2019 Q1, Q2, Q3, Q4, 2020 |  | donors
|  |  | 56 | Meetings of the EITI MSG responsible mining working group | Meetings, discussions | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat, MSG working group, state bodies | Q1, Q2, Q3, Q4, 2019 Q1, Q2, Q3, Q4, 2020
|  |  | 57 | Review of the Roadmap on Introduction of Responsible Mining Practices | Reviewed Roadmap | MSG working group, RA Prime Minister's Staff/ARM-EITI Secretariat | Q4, 2019
Strengthening capacities of the EITI MSG and stakeholder bodies, EITI mainstreaming, encouraging systematic data disclosure
|  |  | 58 | Trainings for the representatives of mining companies and state bodies on use of online EITI reporting platform | Trainings | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat, selected organization, IA | Q2, 2019, Q2, 2020 | 4000 | World Bank, donors
|  | 4.9. c) | 59 | Development and approval of a ToR for a feasibility study of the systematic data disclosure according to the Open Data Principle, election of relevant organization. | ToR, contract | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat | Q2, 2019 |  | State Budget
|  |  | 60 | Preparation of a feasibility study of the systematic data disclosure according to the Open Data Principle, mapping of data for systematic disclosure using the EITI toolkit, development and approval of a roadmap for institutionalization of data disclosure process | Study, mapping with EITI toolkit, roadmap/action plan of activities | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat, selected organization | Q2, Q3, 2019 | 8000 | World Bank
|  |  | 61 | Implementation of the roadmap/action plan for institutionalization of data disclosure process | roadmap/ action plan of activities | MSG, RA Prime Minister's Staff/ARM-EITI Secretariat | Q4, 2019 Q1, Q2, Q3, Q4, 2020 |  | GIZ, donors
STATUS OF ACTIVITIES
Completed
Open
Ongoing