## 2023-2024
The National Priorities of EITI Armenia
1. Deepening the implementation of EITI transparency and accountability Standard in the mining sector, addressing the identified gaps 2. Development of institutional capacities of the stakeholders of the sector, introduction of systematic disclosures, building capacity for using and analyzing disclosed data 3. Ensuring awareness about the mining sector 4. Enhancing the culture of responsible mining through application of the best international practices and improving legal regulations 5 Enhancing competitive investment environment for responsible investors
2023-2024 EITI WORK PLAN OF ARMENIA
Approved by the MSG on 29 June, 2023
Objective | Rationale: Governance-related challenges and obstacles in the mining sector | EITI Standard requirement | No. | Activity | Outcome/Output | Responsible Party(s) | Timeline | 2023-2024 Planned Costs, USD | Funding Source | Risk assessment (low (L), moderate (M), high (H))
Ensuring accessible and timely information | Lack or non-systemic character of the accessible, up-to-date, full and user-friendly information at the primary sources
|  | 7.2 | 1 | Posting up-to-date information/data on the EITI Armenia website, Public awareness and coverage of the EITI processes and recorded results (through social media, mass media, TV broadcasts) | Reports, progress reports, video-clips, publications, legal acts, news items, information on the mining sector and EITI broadcasted and published by social media | Arm-EITI Secretariat/PM's Office, MSG | 2023 2024 |  | State Budget | Լ
|  | 7.2 | 2 | Maintenance of the EITI Armenia website and EITI online reporting platform | Operational website and online reporting platform | Arm-EITI Secretariat/PM's Office, EKENG | 2023 2024 |  | State Budget | Լ | Կայքի կոդերի փոխանցում Վարչապետի աշխատակազմին
|  | 7.1 | 3 | Publication of user friendly information/data on the mining sector and EITI Armenia, preparation of public service announcements (PSAs) | Information sheets, infograms, EITI semi-annual and annual progress reports, EITI report, EITI brief report, informative video-clips | MSG, Arm-EITI Secretariat/PM's Office | 2023 2024 | 25000 | World Bank, State Budget, donors | Լ
|  | 7.2 | 4 | Consultations on the online submission of EITI public reports | Reports published on the EITI Armenia online reporting platform | Arm-EITI Secretariat/PM's Office, selected company | 2023 2024 |  | State Budget | Լ
|  | 7.1 | 5 | Implementation of awareness raising activities, working meetings with stakeholders | Meetings, including with regional and community stakeholders, educational institutions and the general public | MSG, Arm-EITI Secretariat/PM's Office | 2023 2024 | 20000 | World Bank, State Budget, donors | Լ
|  | 7.1 | 6 | Official presentation of the 5th EITI report for 2022 FY / EITI conference | EITI Conference | MSG, Arm-EITI Secretariat/PM's Office | Q4, 2023 - Q1, 2024 | 8000 | World Bank, State Budget | Լ
|  | 7.1 | 7 | Summary event presenting activites implemented with the support of the World Bank grant | EITI Public Event | MSG, Arm-EITI Secretariat/PM's Office | Q1, 2024 | 5000 | World Bank, State Budget | Լ
|  | 7.1 | 8 | Participation in the EITI Global Conference | Meetings with representatives of partner countries, officials from the EITI International Secretariat, Board, cooperation agreements | MSG, Arm-EITI Secretariat/PM's Office | 2023 | 5000 | World Bank, State Budget | Լ
Increasing public accountability and oversight, reducing corruption risks
Maintaining Armenia EITI membership status | Decreased interest among the EITI implementation stakeholders
|  | 7.3 7.4 | 9 | Works on elimination of legal and procedural gaps in the metal mining sector, recorded in the EITI reports | Working groups meetings, discussions, recommendations, draft legal acts | MSG working groups, State agencies, Arm-EITI Secretariat/PM's Office | 2023 2024 |  | State Budget | M
|  |  | 10 | Establishment of MSG working groups to address recorded gaps | Working groups | MSG working groups, State agencies, Arm-EITI Secretariat/PM's Office | 2023 2024 |  | State Budget | Լ
|  | 1.4 | 11 | Holding MSG meetings | MSG meetings | MSG, Arm-EITI Secretariat/PM's Office | Q2, Q3, Q4 - 2023 Q1, Q2, Q3, Q4 - 2024 |  | State Budget | M
|  | 1.4 | 12 | Holding MSG working group meetings | Meetings | MSG working groups, State agencies, Arm-EITI Secretariat/PM's Office | 2023 2024 |  | State Budget | Լ
|  | 1.4 | 13 | Nomination of the MSG new members and approval of the MSG composition | RA Prime Minister Decree, MSG | MSG constiuencies, MSG, Arm-EITI Secretariat/PM's Office | Q1-Q3, 2023 |  |  | Լ/M
|  | 1.4.b | 14 | Amendments to the MSG ToRs (as needed) | MSG ToRs | MSG, Arm-EITI Secretariat/PM's Office | 2023 2024 |  |  | Լ/M
|  | 7.1 | 15 | Participation in EITI Board meetings and conferences | EITI Board meetings | MSG, Arm-EITI Secretariat/PM's Office | 2023 2024 | 4000 | World Bank, State Budget, donors | H/M
|  | 1.5 | 16 | Development and approval of Armenia's 2022 EITI Work plan implementation document | EITI Armenia 2022 Work Plan implementation document | MSG, Arm-EITI Secretariat/PM's Office | Q1, 2023 |  | State Budget | Լ
|  | 1.5 | 17 | Development and approval of Armenia's 2023-2024 EITI Work plan | EITI Armenia 2023-2024 Work Plan | MSG, Arm-EITI Secretariat/PM's Office | Q1, 2023 Q1, 2024 |  | State Budget | Լ
|  |  | 18 | Collaboration with partner and donor organisations | Meetings with donors and partners | MSG, Arm-EITI Secretariat/PM's Office | 2023 2024 |  |  | Լ
|  |  | 19 | Operation of the EITI Armenia Secretariat | EITI implementation documents, reports, work plans, organisation of meetings, support to MSG, local and international cooperation activities, provision of consultancy, State budget documents, reports, ensuring of procurement procedures, fiduciary functions of WB Grant project | MSG, Arm-EITI Secretariat/PM's Office | 2023 2024 | 14000 | World Bank, State Budget | Լ
|  | 1.4 7.4 | 20 | Preparation of EITI Armenia 2022 Annual Progress Report and approval by the MSG | EITI Armenia 2022 Annual Progress Report | MSG, Arm-EITI Secretariat/PM's Office | Q2 - 2023 |  | State Budget | Լ
|  | 1.4 7.4 | 21 | Preparation of EITI Armenia Quarterly/semi-annual Progress Reports and approval by the MSG | Quarterly/ semi-annual progress reports | MSG, Arm-EITI Secretariat/PM's Office | Q1, Q2, Q3, Q4, 2023 Q1, Q2, Q3, Q4, 2024 |  |  | Լ
|  | 1.4 | 22 | Cooperation with the EITI International Secretariat and EITI member countries | Correspondence, meetings, conference calls, online discussions, visits | MSG, Arm-EITI Secretariat/PM's Office | 2023 2024 |  |  | Լ
|  | 1.4 7.4 | 23 | Preparations for the 2nd validation of Armenia, completion of the pre-validation checklists according to the new model of validation | Meetings and discussions with the MSG and MSG costituencies, draft pre-validation checklists | MSG, Arm-EITI Secretariat/PM's Office | Q1 - Q2, 2023 |  | State Budget | Լ
|  | 1.4 7.4 | 24 | Approval of pre-validation templates of the 2nd Validation and submission to the EITI International Secretariat | Approved pre-validation templates, MSG meeting | MSG, Arm-EITI Secretariat/PM's Office | June, 2023 |  |  | Լ
|  |  | 25 | Works with the validation team of the EITI International Secretariat | Correspondence, meetings, conference calls, online meetings of international working group | MSG, Arm-EITI Secretariat/PM's Office | Q3 - Q4, 2023 |  |  | Լ
|  | 7.4 | 26 | Implementation of corrective actions according to the validation assessment (if any) | Meetings of working groups, recommendations for closing gaps | MSG, Arm-EITI Secretariat/PM's Office | Q3 - Q4, 2023 |  |  | Լ/M
|  |  | 27 | Payment of EITI membership contribution |  | MSG, Arm-EITI Secretariat/PM's Office | Q3, 2023 Q3, 2024 | 20000 | State Budget | Լ
Preparation of the EITI Reports in accordance with the EITI Standard | Insufficient Financing
|  | 4.8 4.9 7.2 7.3 | 28 | Preparation of the 4th EITI Armenia Report for 2020-2021 FY | Published report, Summary data template | Independent Administrator, MSG, Arm-EITI Secretariat/PM's Office | January, 2023 |  | World Bank, State Budget | Լ
|  | 7.2 7.3 | 29 | Preparation of the ToRs for the Independent Administrator for the 5th EITI Armenia Report (considering transitional recommendations from the EITI International Secretariat) and approval by the MSG | IA draft ToRs | MSG, Arm-EITI Secretariat/PM's Office | Q1-Q2, 2023 |  | State Budget | Լ
|  |  | 30 | Selection of the Independent Administrator (Tender and approval) | Tender announcement for Independent Administrator, tender, contract awarded to the Independent Administrator | MSG, Arm-EITI Secretariat/PM's Office | Q2-Q3, 2023 |  |  | Լ/M
|  | 4.8 4.9 7.2 7.3 | 31 | Preparation of the 5th EITI Armenia Report for 2022 FY | EITI draft Report, EITI Report of Armenia, Summary data template | Independent Administrator, MSG, Arm-EITI Secretariat/PM's Office | Q3-Q4, 2023 | 60000 | World Bank, State Budget | Լ/M
|  |  | 32 | Discussion of the new requirements of the 2023 EITI Standard in order to find out their relevance to the Armenian EITI | Meetings, recommendations | MSG, Arm-EITI Secretariat/PM's Office, State Agencies | Q3, Q4, 2023 2024 |  | State Budget | M
|  | 7.2 7.3 | 33 | Preparation of the ToRs for the Independent Administrator for the 6th EITI Armenia Report (considering transitional recommendations from the EITI International Secretariat) and approval by the MSG | IA draft ToRs | MSG, Arm-EITI Secretariat/PM's Office | Q1-Q2, 2024 |  | State Budget | H
|  |  | 34 | Selection of the Independent Administrator | Contract awarded to the Independent Administrator | MSG, Arm-EITI Secretariat/PM's Office | Q2-Q3, 2024 |  |  | H
|  | 4.8 4.9 7.2 7.3 | 35 | Preparation of the 6th EITI Armenia Report for 2023 FY | EITI draft Report, EITI Report of Armenia, Summary data template | Independent Administrator, MSG, Arm-EITI Secretariat/PM's Office | Q4, 2024 |  |  | H
In the scope of "Opening Extractives" Programme implementation of BO data verification tools and strengthening stakeholder capacity to use data
|  | 2.5 7.1 | 36 | Implementation of agreed activities within the framework of the "Opening Extractives" project of EITI and OpenOwnership | Events, training, discussions of recommendations of international consultants, their implementation | Ministry of Justice/State Registry, MSG, Arm-EITI Secretariat/PM's Office,EITI International Secretariat, OpenOwnership, other interested bodies | 2023 2024 |  |  | L
|  | 2.5 7.1 | 37 | In the scope of the “Opening Extractives” programme participation in training programs and discussions on BO data verification and other related topics | Training, discussions organized by international consultants | Ministry of Justice/State Registry, MSG, Arm-EITI Secretariat/PM's Office | 2023 2024 |  |  | L
|  | 2.5 | 38 | Ongoing monitoring of BO declarations, their completeness and accuracy of BO data in the mining sector | Review of declarations, submission of recommendations to authorized bodies | MSG, Arm-EITI Secretariat/PM's Office | 2023 2024 |  |  | L
|  |  | 39 | Fulfillment of the 2.5th requirement of the EITI Standard and the recommendations of its validation assessment | Draft legal acts | BO working group, Ministry of Justice, MSG, Arm-EITI Secretariat/PM's Office | 2023 2024 |  |  | L
Establishment of EITI data systematic disclosures IT system, strengthening the capacity of the MSG and stakeholders | Lack of legal, institutional and technical capacity to carry out systematic disclosures, insufficient financing for development of a comprehensive SDD IT system
|  | 4.8/4.9 7.2 | 40 | Preparation of the ToRs for the Systematic data disclosure (SDD) IT system | Draft ToR | MSG, Arm-EITI Secretariat/PM's Office, consultant, EKENG, working group | Q4, 2022 Q1, 2023 | 6000 | World Bank, State Budget | L
|  |  | 41 | Approval of the ToRs for the Systematic data disclosure (SDD) IT system | ToR | MSG, State bodies | Q1, 2023 |  |  | L
|  |  | 42 | Selection of the compamy for development of the SDD IT system | contract | MSG, Arm-EITI Secretariat/PM's Office | Q2, 2023 |  | World Bank, State Budget | M
|  |  | 43 | Development of the SDD IT system | SDD IT system | selected company, MSG, Arm-EITI Secretariat/PM's Office, consultant, EKENG, working group | Q3, Q4, 2023 2024 | 150000 | World Bank, State Budget | M
|  |  | 44 | Drafting legislative amendments required to implement systematic disclosures | Meetings, discussions, draft legal acts | MSG, State bodies, consultant, Arm-EITI Secretariat/PM's Office | Q2, Q3, 2024 | 7000 | World Bank, State Budget | M
|  |  | 45 | Submission of the legal package including amendments to the RA government decision N 666 dated 08.06.2018 to the Government of the Republic of Armenia | Draft legal acts | MSG, State bodies, consultant, Arm-EITI Secretariat/PM's Office | Q3-Q4, 2023 |  |  | M
|  |  | 46 | Implementation of systematic disclosures - testing of SDD IT portal and respective agency pages | Systematic disclosures | State bodies, EKENG,Arm-EITI Secretariat/PM's Office, selected company, working group | Q4, 2023 2024 | see activity 43 | World Bank, State Budget | M
|  |  | 47 | Launch of the SDD IT system, ensuring public access to data | SDD system, launched portal, systematic disclosures Տ | State bodies, EKENG,Arm-EITI Secretariat/PM's Office, selected company | 2024 | see activity 43 | World Bank, State Budget | M
Strengthening the capacity to use EITI data
|  | 7.1 | 48 | Capacity building activities for the Parliament representatives | Meetings, training | MSG, Arm-EITI Secretariat/PM's Office, consultant | 2023 2024 | 20000 | World Bank, State Budget | L
|  |  | 49 | Capacity building activities for the representatives of State agencies | Meetings, training | MSG, Arm-EITI Secretariat/PM's Office, consultant | 2023 2024 |  | World Bank, State Budget | L
|  |  | 50 | Capacity building activities for the affected communities' representatives to develop effective participation, sustainable development programs and policy preparation skills | Meetings, training | MSG, Arm-EITI Secretariat/PM's Office, consultant | 2023 2024 |  | World Bank, State Budget | L
|  |  | 51 | Mining and EITI data analytical capacity building activities for CSOs, Media representatives and academic community | Meetings, training | MSG, Arm-EITI Secretariat/PM's Office, consultant | 2023 2024 |  | World Bank, State Budget | L
Implementation of responsible mining practices, ensuring stakeholder participation in the implementation of the Mining Strategy action plan | Lack of responsible mining culture, deficiency of relevant legal framework, insufficient capacity of relevant state agencies, mining companies and civil society
|  | 1 7.1 | 52 | Restructuring of the working group to Support the Implementation of Responsible Mining Practices | Working group | MSG working groups, MTAI, State agencies, MSG Arm-EITI Secretariat/PM's Office | Q3, 2023 |  |  | M
|  |  | 53 | Holding meetings of the working group to support the implementation of responsible mining practices, developing the action plan of the working group, presenting recommendations within the framework of the implementation of the Mining Strategy action plan, recommendations for legislative reforms | Meetings, Action plan, recommendations, draft legal acts | MSG working groups, MTAI, State agencies, MSG Arm-EITI Secretariat/PM's Office | Q3, Q4, 2023, 2024 |  | State Budget Donors | M
STATUS OF ACTIVITIES
Completed
Open
Ongoing