## Sheet1
As part of implementing the Extractive Industries Transparency Initiative (EITI) in the Republic of Armenia, Armenia's EITI MSG has identified the below National Priorities: 1. Ensuring awareness about the mining sector 2. Increasing the mining sector transparency and accountability 3. Enhancing the culture of responsible mining through application of the best international practices, and based on legal regulations 4. Enhancing competitive investment environment for responsible investors 5. Institutional capacity development of sector beneficiaries
2017-2018 EITI WORK PLAN OF ARMENIA
Objective | Rationale: Governance-related challenges and obstacles in the sector | EITI Standard requirement | No. | Activity | Outcome/Output | Responsible Party | Timeline | Cost, USD | Funding Source
Ensuring accessible and timely information | Availability of accessible, timely and comprehensive information on the mining sector and EITI
|  |  | 1 | Developing the terms of reference (ToR) for the EITI website, conducting tender for selection of organization, approval of the organization | ToR, contract with the organization | MSG, RA Government Staff/ARM-EITI Secretariat | May - 2017 Oct - 2017 | 1000 | State budget
|  |  | 2 | Creating the RA EITI website | RA EITI website, databases, database processing tools for providing on-line access to information, conducting inquiries, free information viewing functionality, creation of on-line reporting portal | RA Government Staff/ARM-EITI Secretariat, selected organization | 2018-02-01 | 60000 | World Bank, other donors, State budget
|  |  | 3 | Ongoing website support |  | Selected organization | Ongoing | 10000 | World Bank, other donors, State budget
|  | requirement 7.1 | 4 | Posting appropriate information in the EITI website (reports, videos, protocols) | Reports, videos, protocols published in the website | MSG, RA Government Staff/ARM-EITI Secretariat | Ongoing
|  | requirement 7.1 | 5 | Disclosure and publication of information on the mining sector in an easily understood language, preparation of social advertising | Information sheets, infograms, EITI report, MSG annual report, information video-clips | MSG, RA Government Staff/ARM-EITI Secretariat | Ongoing | 45000 | World Bank, other donors, State budget
|  |  | 6 | Awareness campaign on mining sector and EITI and their elucidation via social media (YouTube, Twitter, Facebook, etc.) | Information about mining and EITI published in social media | MSG, RA Government Staff/ARM-EITI Secretariat | Ongoing
|  |  | 7 | Development of communication strategy | Draft communication strategy | MSG, RA Government Staff/ARM-EITI Secretariat, expert | 2017-05-01 | 2000 | Donors
|  |  | 8 | Approval of communication strategy | Communication strategy | MSG | 2017-06-01
|  | requirement 7.1 | 9 | Implementation of awareness raising measures | Round tables, meetings, including with representatives of affected communities, meetings with educational institutions | MSG, RA Government Staff/ARM-EITI Secretariat | Ongoing | 10000 | World Bank, other donors, partners, State budget
|  | requirement 7.1 | 10 | Official presentation of EITI report / conference | EITI conference | MSG, RA Government Staff/ARM-EITI Secretariat, EITI Int. Secretariat | 2018-10-01 | 15000 | World Bank, other donors, partners, State budget
Development of roadmap for disclosure of ultimate beneficial owners | Reducing corruption risks, improving the investment environment and accountability | requirement 2.5
|  |  | 11 | Development of roadmap for disclosure of ultimate beneficiary owners | Draft roadmap | MSG, RA Government Staff/ARM-EITI Secretariat, RA government agencies | 2017-06-01 | 7000 | Donors, State budget
|  |  | 12 | Public consultations on the draft roadmap | Disclosure of the draft roadmap, meetings | MSG, RA Government Staff/ARM-EITI Secretariat | 2017-07-01 | 1000 | Donors, partners, State Budget
|  |  | 13 | Approval of the roadmap for disclosure of ultimate beneficiary owners | Roadmap | MSG | 2017-08-01
|  |  | 14 | Submission of the roadmap for disclosure of ultimate beneficiary owners to the EITI Secretariat | Roadmap submitted to the EITI Secretariat | RA Government Staff/ARM-EITI Secretariat | 2017-09-01
Review of the legal framework of Armenia, disclosure of inconsistencies and gaps with EITI Standard | Alignment of the Armenian legal framework for the purpose of implementing the EITI standard | requirement 2
|  |  | 15 | Preparation of the terms of reference by the MSG based on which local and international consultants will conduct a review for identifying inconsistencies | Terms of reference | MSG, RA Government Staff/ARM-EITI Secretariat | 2017-04-01 | 1000 | State Budget
|  |  | 16 | Review of legislation, identification of gaps, submission of recommendations on addressing the gaps | Report, action plan | MSG, RA Government Staff/ARM-EITI Secretariat, expert | 2017-12-01 | 15000 | donors
|  |  | 17 | Submission of the report and action plan to the MSG |  | RA Government Staff/ARM-EITI Secretariat, expert | 2017-12-01
|  |  | 18 | Review and approval of report and action plan by the MSG | Report, action plan | MSG, RA Government Staff | 2017-12-01
Review of the best international practices and development of roadmap for harmonization with the EITI and best responsible mining international experience | Implementation of responsible mining behavior | requirement 8.3.a.iii.
|  |  | 19 | Development and approval of the terms of reference | Terms of reference | MSG, RA Government Staff/ARM-EITI Secretariat | 2017-10-01 | 1000 | State budget
|  |  | 20 | Development of roadmap for reviewing international experience | Roadmap | MSG, RA Government Staff/ARM-EITI Secretariat | 2017-11-01 | 5000 | Donors
|  |  | 21 | Approval of the roadmap by the MSG | Action plan, budget | MSG | 2018-01-01
|  |  | 22 | Implementation of action plan |  | MSG, RA Government Staff/ARM-EITI Secretariat, RA government agencies | 2018-12-01 | 50000 | World Bank, other donors, partners
|  |  | 23 | Involvement in development of the sector policy | Involvement, provision of feedback | MSG, RA Government Staff/ARM-EITI Secretariat | Ongoing
Ensuring Armenia's EITI candidacy status | Implementation of the EITI standard
|  | requirement 1.1 | 24 | RA Prime Minister's statement | Statement |  | 2015-07-01
|  | requirement 1.4.b. ii. | 25 | EITI awareness raising events | Meetings |  | 2015-12-01
|  | requirement 1.2 requirement 1.3 | 26 | Nomination of MSG members | Nominated MSG members | MSG sub-groups | 2016-06-01
|  |  | 27 | Training seminars for MSG members | Training seminars | MSG, RA Government Staff, donors, experts | Mar-16 - Nov-16
|  | requirement 1.4.b | 28 | Development of the ToR of the MSG | draft ToR of the MSG | MSG, RA Government Staff | 2016-09-01
|  | requirement 1.4.b | 29 | Approval of the ToR of the MSG | ToR of the MSG | MSG | 2016-12-01
|  | requirement 1.4 | 30 | Participation in EITI Board meetings | EITI Board meetings | MSG, RA Government Staff
|  | requirement 1.4 | 31 | MSG meeting | MSG meeting | MSG, RA Government Staff | 27.06.2016
|  |  | 32 | First official meeting of MSG, launching event | Firts official meeting of MSG, launching event | MSG, RA Government Staff | 25.11.2016
|  | requirement 1.4.a. iii. | 33 | Adoption of RA Prime Minister Decree on Setting Up the RA EITI Multi-Stakeholder Group and Approving Its Composition | RA Prime Minister decree | RA Government Staff | 24.11.2016
|  | requirement 1.5 requirement 1.4.b.iv. | 34 | Development of Armenia's EITI work program | Armenia's draft EITI work program | MSG, RA Government Staff | 2016-12-01
|  | requirement 1.5 requirement 1.4.b.iv. | 35 | Approval of Armenia's EITI work program | Armenia's EITI work program | MSG | 2016-12-01
|  | requirement 1.4 | 36 | Development of the RA EITI candidature application | Draft RA EITI candidacy application | MSG, RA Government Staff | 2016-12-01
|  | requirement 1.4 | 37 | Approval of the RA EITI candidature application | RA EITI candidacy application | MSG | 2016-12-01
|  |  | 38 | Collaboration with donors | Meetings with donors | RA Government Staff | Ongoing
|  | requirement 1.4 | 39 | Submission of the RA EITI candidature application to the EITI international secretariat | Submitted RA EITI candidacy application | RA Government Staff | 2016-12-01
|  |  | 40 | Establishment and operation of the Armenian EITI secretariat | Armenian EITI secretariat | RA Government Staff | Oct - 2017- Dec - 2018 | 120000 | World Bank, State budget
|  | requirement 1.4.b.iv. requirement 7.4 | 41 | Preparation and approval of the RA EITI MSG annual report | Annual report of the RA EITI MSG | MSG, RA Government Staff/ARM-EITI Secretariat | Jan - 2018 Jan - 2019
|  | requirement 1.4.b.iv. requirement 7.4 | 42 | Preparation of monitoring reports on the RA EITI MSG activities, EITI implementation, action plan (quarterly, biannual, annual) | Reports | MSG, RA Government Staff/ARM-EITI Secretariat | Quarterly
|  | requirement 1.4 | 43 | Collaboration with the EITI international secretariat and other EITI member countries | Correspondence, meetings, conference calls | RA Government Staff/ARM-EITI Secretariat, MSG | Ongoing
|  |  | 44 | Participation in EITI Board meetings and conferences |  | MSG, RA Government Staff/ARM-EITI Secretariat | Ongoing | 70000 | World Bank, other donors
|  | requirement 1.4 | 45 | Holding of the RA EITI MSG meetings | RA EITI MSG meetings | RA Government Staff/ARM-EITI Secretariat, MSG | Quarterly | 2000 | State budget
|  | requirement 1.5.f | 46 | Revision and approval of the EITI work plan | Revised EITI work plan | MSG, RA Government Staff/ARM-EITI Secretariat | Jan - 2018 Jan - 2019
|  |  | 47 | Creation of MSG working groups |  | MSG | Ongoing
|  |  | 48 | Development and approval of the 2019-2020 EITI work program | 2019-2020 EITI work program | MSG, RA Government Staff/ARM-EITI Secretariat | 2018-10-01
|  |  | 49 | Payment of EITI membership fee |  |  | Dec - 2017 Dec - 2018 | 20000 | State budget
Comprehensive report consistent with the EITI standard | Presentation of report under the EITI standard, publication of comprehensive information on the sector
|  |  | 50 | Scoping study of EITI report | scoping study | RA Government Staff/ARM-EITI Secretariat, MSG | 2017-06-01 | 1000 | State budget
|  | requirement 1.4.b.iv. | 51 | Developing the ToR for the independent administrator | Draft ToR for the independent administrator | RA Government Staff/ARM-EITI Secretariat, MSG, RA government agencies | 2017-07-01 | 1000 | State budget
|  | requirement 4.9. b.iii | 52 | Discussion and approval of the ToR for the independent administrator | ToR for the independent administrator | MSG, RA Government Staff/ARM-EITI Secretariat | 2017-08-01
|  | requirement 1.4.b.iv. | 53 | Selection of the independent administrator (tender and approval) and preparation of the EITI report of Armenia | Tender announcement for independent administrator, tender, contract awarded to the independent administrator, draft EITI report of Armenia | RA Government Staff/ARM-EITI Secretariat, MSG, independent administrator | Oct-2017-July-2018 | 100000 | World bank
|  |  | 54 | Preparation and approval of the list of reporting government agencies and entities by the MSG, definition of materiality | List of reporting government agencies and entities | RA Government Staff/ARM-EITI Secretariat, MSG, RA government agencies | 2017-11-01
|  |  | 55 | Development and approval of the format and timing of presentation of reporting by government agencies and extractive entities for the EITI Report purposes | Reporting format | RA Government Staff/ARM-EITI Secretariat, MSG, RA government agencies | 2017-11-01
|  |  | 56 | Training for government agencies and extractive entities on presentation of reports for the EITI report purposes | Training | RA Government Staff/ARM-EITI Secretariat, MSG, RA government agencies | 2017-12-01 | 5000 | State budget
|  |  | 57 | Discussion with the government of the need for legal bases for reporting | Discussion | RA Government Staff, MSG | 2017-11-01
|  |  | 58 | Discussion and approval of the RA EITI report prepared by the independent administrator | RA EITI Report | MSG,RA Government Staff/ARM-EITI Secretariat | 2018-07-01
|  |  | 59 | Translation work |  |  | Ongoing | 10000 | World bank, other donors, State budget
|  |  | 60 | Submission of the RA EITI Report to the EITI Secretariat and its publication | RA EITI Report | RA Government Staff/ARM-EITI Secretariat, MSG | 2018-08-01
|  | requirement 7.3 | 61 | Review of considerations of the EITI Secretariat concerning the RA EITI Report and preparation of report on these considerations | Report | RA Government Staff/ARM-EITI Secretariat, MSG | 2018-12-01
STATUS OF ACTIVITIES
Accomplished
Open
Ongoing
Armenian EITI MSG members
Armenian EITI MSG members from RA Government constituency
| MSG Chairman |  |  |  | Davit Harutyunyan
Karen Isakhanyan
Tigran Khachatryan
Davit Ananyan
Khachik Hakobyan
Vardan Gevorgyan
Armenian EITI MSG members from the mining companies' constituency
Pertsh Khachatryan
Vahe Vardanyan
Armen Stepanyan
Artur Nikoghosyan
Armenian EITI MSG members from civil society constituency
Sona Ayvazyan
Artur Grigoryan
Erik Grigoryan
Inga Zarafyan
Harutyun Movsisyan