## Sheet1
As part of implementing the Extractive Industries Transparency Initiative (EITI) in the Republic of Armenia, Armenia's EITI MSG has identified the below National Priorities: 1. Ensuring awareness about the mining sector 2. Increasing the mining sector transparency and accountability 3. Enhancing the culture of responsible mining through application of the best international practices, and based on legal regulations 4. Enhancing competitive investment climate for responsible investors 5. Institutional capacity development of the sector beneficiaries
2017-2018 EITI WORK PLAN OF ARMENIA (reviewed in March 2018)
Objective | Rationale: Governance-related challenges and obstacles in the sector | EITI Standard requirement | No. | Activity | Outcome/Output | Responsible Party | Timeline | Cost, USD | Funding Source
Ensuring accessible and timely information | Availability of accessible, timely and comprehensive information on the mining sector and EITI
|  |  | 1 | Developing the terms of reference (ToR) for the EITI website, conducting tender for selection of organization, approval of the organization | ToR, contract with the organization | MSG, RA Government Staff/ARM-EITI Secretariat | Nov-Dec-17 | 1000 | State budget
|  |  | 2 | Creating the RA EITI website | RA EITI website, databases, database processing tools for providing online access to information, conducting inquiries, free information viewing functionality, creation of online reporting portal | RA Government Staff/ARM-EITI Secretariat, selected organization | Jan - June-18 | 16000 | UNDP, State budget
|  |  | 3 | Ongoing website support |  | Selected organization, RA Government Staff | Ongoing | included in funding of 2nd activity | UNDP, State budget
|  | requirement 7.1 | 4 | Posting appropriate information in the EITI website (reports, videos, protocols) | Reports, videos, protocols published in the website | MSG, RA Government Staff/ARM-EITI Secretariat | Ongoing
|  | requirement 7.1 | 5 | Disclosure and publication of information on the mining sector in an easily understood language, preparation of social advertising | Information sheets, infograms, EITI report, MSG annual report, information video-clips | MSG, RA Government Staff/ARM-EITI Secretariat | Ongoing | 11500 | World Bank
|  |  | 6 | Awareness campaign on mining sector and EITI and their elucidation via social media (YouTube, Twitter, Facebook, etc.) | Information about mining and EITI published in social media | MSG, RA Government Staff/ARM-EITI Secretariat | Ongoing
|  |  | 7 | Development of communication strategy | Draft communication strategy | MSG, RA Government Staff/ARM-EITI Secretariat, expert | 2018-04-01 | 54000 | The British Embassy in Yerevan | The same Project is also funding activities N 16, N 20, N 50 and N 51
|  |  | 8 | Approval of communication strategy | Communication strategy | MSG, AUA CRM RA Government Staff/ARM-EITI Secretariat | 2018-05-01
|  | requirement 7.1 | 9 | Implementation of awareness raising measures | Round tables, meetings, including with representatives of affected communities, meetings with educational institutions | MSG, RA Government Staff/ARM-EITI Secretariat | Ongoing | 5000 | World Bank, State budget
|  | requirement 7.1 | 10 | Official presentation of EITI report / conference | EITI conference | MSG, RA Government Staff/ARM-EITI Secretariat, EITI Int. Secretariat | 2018-10-01 | 8000 | World Bank, State budget
Development of roadmap for disclosure of ultimate beneficial owners | Reducing corruption risks, improving the investment environment and accountability | requirement 2.5
|  |  | 11 | Development of roadmap for disclosure of ultimate beneficial owners | Draft roadmap | MSG, RA Government Staff/ARM-EITI Secretariat, RA government agencies | Nov-Dec-17 | 23800 | EBRD
|  |  | 12 | Public consultations on the draft roadmap | Disclosure of the draft roadmap, meetings | MSG, RA Government Staff/ARM-EITI Secretariat | Ongoing | 1000 | Donors, partners, State Budget
|  |  | 13 | Approval of the roadmap for disclosure of ultimate beneficial owners | Roadmap | MSG | 2017-12-01
|  |  | 14 | Submission of the roadmap for disclosure of ultimate beneficial owners to the EITI Secretariat | Roadmap submitted to the EITI Secretariat | RA Government Staff/ARM-EITI Secretariat | 2017-12-01
|  |  | 14.1 | Establishment of an Interagency Work Group (WG) for BO disclosure and legal framework development meetings | Interagency Work Group, meetings | RA Government Staff/ARM-EITI Secretariat, MSG, WG | March-May-18 | 1000 | State Budget
|  |  | 14.2 | Circulation of the legislative package on BO disclosure, submission to the Government of the Republic of Armenia, then the RA National Assembly | Legislative package on BO disclosure | RA Government Staff/ARM-EITI Secretariat, MSG, WG | May-Oct-2018 | 7000 | World Bank
|  |  | 14.3 | Discussions of the legislative package on BO disclosure with the stakeholders | Meetings | RA Government Staff/ARM-EITI Secretariat, MSG, WG | April-Oct-2018 | 2500 | World Bank
|  |  | 14.4 | A study on the expediency of expanding the scope of the BO disclosure in the following years and development of the roadmap | Reviewed BO roadmap | MSG, RA Government Staff/ARM-EITI Secretariat | 2018-12-01
Review of the legal framework of Armenia, disclosure of inconsistencies and gaps with EITI Standard | Alignment of the Armenian legal framework for the purpose of implementing the EITI standard | requirement 2
|  |  | 15 | Preparation of the terms of reference by the MSG based on which local and international consultants will conduct a review for identifying inconsistencies | Terms of reference | MSG, RA Government Staff/ARM-EITI Secretariat | June-July-2017 | 1000 | State Budget
|  |  | 16 | Review of legislation, identification of gaps, submission of recommendations on addressing the gaps | Report, action plan | AUA CRM, MSG, RA Government Staff/ARM-EITI Secretariat, expert | 2018-05-01 | Included in funding of 7th activity | The British Embassy in Yerevan
|  |  | 17 | Submission of the report and action plan to the MSG |  | AUA CRM, RA Government Staff/ARM-EITI Secretariat | 2018-05-01
|  |  | 18 | Review and approval of report and action plan by the MSG | Report, action plan | MSG | 2018-06-01
|  |  | 18.1 | Study on possibility of project level reporting in the future EITI Reports,and the development of a roadmap for the project level reporting and the recommendations of the first EITI report | Study, roadmap | MSG, RA Government Staff/ARM-EITI Secretariat, IA | June-Nov-2018 | 1000 | State Budget
|  |  | 18.2 | Approval of the roadmap by the MSG | Roadmap | MSG | 2018-12-01
Review of the best international practices and development of roadmap for harmonization with the EITI and best international experience regarding the responsible mining | Implementation of responsible mining behavior | requirement 8.3.a.iii.
|  |  | 19 | Development and approval of the terms of reference | Terms of reference | MSG, RA Government Staff/ARM-EITI Secretariat | June-July-2017 | 1000 | State budget
|  |  | 20 | Development of roadmap for reviewing international experience | Roadmap | MSG, RA Government Staff/ARM-EITI Secretariat, AUA CRM | 2018-05-01 | uncluded in funding of 7th activity | The British Embassy in Yerevan
|  |  | 21 | Approval of the roadmap by the MSG | Action plan, budget | MSG | 2018-05-01
|  |  | 22 | Implementation of action plan |  | MSG, RA Government Staff/ARM-EITI Secretariat, RA government agencies | 2018-12-01 | 50000 | World Bank, other donors, partners
|  |  | 23 | Involvement in development of the sector policy | Involvement, provision of feedback | MSG, RA Government Staff/ARM-EITI Secretariat | Ongoing
Ensuring Armenia's EITI candidacy status | Implementation of the EITI standard
|  | requirement 1.1 | 24 | RA Prime Minister's statement | Statement |  | 2015-07-01
|  | requirement 1.4.b. ii. | 25 | EITI awareness raising events | Meetings |  | 2015-12-01
|  | requirement 1.2 requirement 1.3 | 26 | Nomination of MSG members | Nominated MSG members | MSG sub-groups | 2016-06-01
|  |  | 27 | Training seminars for MSG members | Training seminars | MSG, RA Government Staff, donors, experts | Mar-16 - Nov-16
|  | requirement 1.4.b | 28 | Development of the ToR of the MSG | draft ToR of the MSG | MSG, RA Government Staff | 2016-09-01
|  | requirement 1.4.b | 29 | Approval of the ToR of the MSG | ToR of the MSG | MSG | 2016-12-01
|  | requirement 1.4 | 30 | Participation in EITI Board meetings | EITI Board meetings | MSG, RA Government Staff
|  | requirement 1.4 | 31 | MSG meeting | MSG meeting | MSG, RA Government Staff | 27.06.2016
|  |  | 32 | First official meeting of MSG, launching event | Firts official meeting of MSG, launching event | MSG, RA Government Staff | 25.11.2016
|  | requirement 1.4.a. iii. | 33 | Adoption of RA Prime Minister Decree on Setting Up the RA EITI Multi-Stakeholder Group and Approving Its Composition | RA Prime Minister decree | RA Government Staff | 24.11.2016
|  | requirement 1.5 requirement 1.4.b.iv. | 34 | Development of Armenia's EITI work program | Armenia's draft EITI work program | MSG, RA Government Staff | 2016-12-01
|  | requirement 1.5 requirement 1.4.b.iv. | 35 | Approval of Armenia's EITI work program | Armenia's EITI work program | MSG | 2016-12-01
|  | requirement 1.4 | 36 | Development of the RA EITI candidature application | Draft RA EITI candidacy application | MSG, RA Government Staff | 2016-12-01
|  | requirement 1.4 | 37 | Approval of the RA EITI candidature application | RA EITI candidacy application | MSG | 2016-12-01
|  |  | 38 | Collaboration with donors | Meetings with donors | RA Government Staff | Ongoing
|  | requirement 1.4 | 39 | Submission of the RA EITI candidature application to the EITI international secretariat | Submitted RA EITI candidacy application | RA Government Staff | 2016-12-01
|  |  | 40 | Establishment and operation of the Armenian EITI secretariat | Armenian EITI secretariat | RA Government Staff/ARM-EITI Secretariat | Oct - 2017- Dec - 2018, ongoing | 90000 | State budget, USAID Armenia
|  | requirement 1.4.b.iv. requirement 7.4 | 41 | Preparation and approval of the RA EITI MSG annual report | Annual report of the RA EITI MSG | MSG, RA Government Staff/ARM-EITI Secretariat | 2018-06-01
|  | requirement 1.4.b.iv. requirement 7.4 | 42 | Preparation of monitoring reports on the RA EITI MSG activities, EITI implementation, action plan (quarterly, annual) | Reports | MSG, RA Government Staff/ARM-EITI Secretariat | Quarterly
|  | requirement 1.4 | 43 | Collaboration with the EITI international secretariat and other EITI member countries | Correspondence, meetings, conference calls | RA Government Staff/ARM-EITI Secretariat, MSG | Ongoing
|  |  | 44 | Participation in EITI Board meetings and conferences |  | MSG, RA Government Staff/ARM-EITI Secretariat | Ongoing | 10000 | World Bank, other donors
|  | requirement 1.4 | 45 | Holding of the RA EITI MSG meetings | RA EITI MSG meetings | RA Government Staff/ARM-EITI Secretariat, MSG | Quarterly | 2000 | State budget
|  | requirement 1.5.f | 46 | Revision and approval of the EITI work plan | Revised EITI work plan | MSG, RA Government Staff/ARM-EITI Secretariat | 2018-03-01
|  |  | 47 | Creation of MSG working groups |  | MSG | Ongoing
|  |  | 48 | Development and approval of the 2019-2020 EITI work program | 2019-2020 EITI work program | MSG, RA Government Staff/ARM-EITI Secretariat | 2018-10-01
|  |  | 49 | Payment of EITI membership fee |  |  | 2018-04-01 | 10000 | State budget
|  |  | 49.1 | Strengthening the capacity of the MSG and stakeholder representatives | trainings, workshops | RA Government Staff/ARM-EITI Secretariat | ongoing | 15000 | World Bank
Comprehensive report consistent with the EITI standard | Presentation of report under the EITI standard, publication of comprehensive information on the sector
|  |  | 50 | Scoping study of EITI report | scoping study | RA Government Staff/ARM-EITI Secretariat, MSG, AUA CRM | Sep-2017-March-2018 | included in funding of 7th activity | The British Embassy in Yerevan
|  | requirement 1.4.b.iv. | 51 | Development of the ToR for the independent administrator | Draft ToR for the independent administrator | RA Government Staff/ARM-EITI Secretariat, MSG, AUA CRM | Jan-March,2018 | included in funding of 7th activity | The British Embassy in Yerevan
|  | requirement 4.9. b.iii | 52 | Discussion and approval of the ToR for the independent administrator | ToR for the independent administrator | MSG, RA Government Staff/ARM-EITI Secretariat | 2018-03-01
|  | requirement 1.4.b.iv. | 53 | Selection of the independent administrator (tender and approval) preparation of the EITI report of Armenia | Tender announcement for independent administrator, tender, contract awarded to the independent administrator | RA Government Staff/ARM-EITI Secretariat, MSG | Apr-May, 2018
|  |  | 53.1 | Preparation of the EITI report of Armenia | EITI report of Armenia | Independent administrator | May-Aug,2018 | 100000 | World bank
|  |  | 54 | Preparation and approval of the list of reporting government agencies and entities by the MSG, definition of materiality | List of reporting government agencies and entities | RA Government Staff/ARM-EITI Secretariat, MSG | 2018-03-01
|  |  | 55 | Development of the draft Government Decision on procedure of submission of EITI e-reports by the government agencies and extractive entities and reporting formats | Reporting formats, draft Government Decision | RA Government Staff/ARM-EITI Secretariat, MSG, IA | Jan-Apr, 2018
|  |  | 55.1 | Submission of the draft Government Decision to the Government | Government Decision | RA Government Staff/ARM-EITI Secretariat | 2018-05-01
|  |  | 56 | Training for government agencies and extractive entities on presentation of reports for the EITI report purposes | Training | RA Government Staff/ARM-EITI Secretariat, MSG,IA, RA government agencies | May-June, 2018 | 2500 | World bank
|  |  | 57 | Discussion with the government of the need for legal bases for reporting | Discussion | RA Government Staff, MSG | 2017-11-01
|  |  | 58 | Discussion and approval of the RA EITI report prepared by the independent administrator | RA EITI Report | MSG,RA Government Staff/ARM-EITI Secretariat | Aug-Sep, 2018
|  |  | 59 | Translation work |  |  | Ongoing | 10000 | World bank, USAID Armneia, State budget
|  |  | 60 | Submission of the RA EITI Report to the EITI Secretariat and its publication | RA EITI Report | RA Government Staff/ARM-EITI Secretariat, MSG | 2018-09-01
|  | requirement 7.3 | 61 | Review of considerations of the EITI Secretariat concerning the RA EITI Report and preparation of report on these considerations | Report | RA Government Staff/ARM-EITI Secretariat, MSG | 2018-11-01
STATUS OF ACTIVITIES
Completed
Open
Ongoing