## Sheet1
As part of implementing the Extractive Industries Transparency Initiative (EITI) in the Republic of Armenia, Armenia's EITI MSG has identified the below National Priorities: 1. Ensuring awareness about the mining sector 2. Increasing the mining sector transparency and accountability 3. Enhancing the culture of responsible mining through application of the best international practices, and based on legal regulations 4. Enhancing competitive investment environment for responsible investors 5. Institutional capacity development of sector beneficiaries
2017-2018 EITI WORK PLAN OF ARMENIA (implementation as of February, 2018)
Objective | Rationale: Governance-related challenges and obstacles in the sector | EITI Standard requirement | No. | Activity | Outcome/Output | Responsible Party | Timeline | Cost, USD | Funding Source | Actual Cost, USD | Actual Funding Source | Status | Implementation
Ensuring accessible and timely information | Availability of accessible, timely and comprehensive information on the mining sector and EITI
|  |  | 1 | Developing the terms of reference (ToR) for the EITI website, conducting tender for selection of organization, approval of the organization | ToR, contract with the organization | MSG, RA Government Staff/ARM-EITI Secretariat | May - 2017 Oct - 2017 | 1000 | State budget |  | State budget | completed | The ToR of Armenia's EITI website were developed in November-December, and approved by the MSG on December 12, 2017.
|  |  | 2 | Creating the RA EITI website | RA EITI website, databases, database processing tools for providing on-line access to information, conducting inquiries, free information viewing functionality, creation of on-line reporting portal | RA Government Staff/ARM-EITI Secretariat, selected organization | 2018-02-01 | 60000 | World Bank, other donors, State budget | 16000 | UNDP, State budget | ongoing | The EITI website and the databases will be stored on the Servers of the Government Staff of RA. 1,461,600 AMD from the state budget has been allocated for the purchase of server storage equipment approved per the RA Government Decree No. 213-N of March 9, 2017. The competition for the development of the Armenian EITI website was announced by the UNDP on December 12, 2017. Helix Consulting LLC was named the winner. An agreement was signed in January, 2018. The EITI website development works must be implemented by May 15, 2018.
|  |  | 3 | Ongoing website support |  | Selected organization | Ongoing | 10000 | World Bank, other donors, State budget |  |  |  | The website maintenance will start after the website’s launch.
|  | requirement 7.1 | 4 | Posting appropriate information in the EITI website (reports, videos, protocols) | Reports, videos, protocols published in the website | MSG, RA Government Staff/ARM-EITI Secretariat | Ongoing |  |  |  |  | ongoing | In 2017, Armenia's EITI experts (EITI Secretariat of Armenia) have updated the EITI webpages on the Government’s official website in Armenian and English. News on EITI implementation activities, quarterly reports, and other documents, as well as the minutes of the EITI MSG meetings were posted on the EITI webpages.
|  | requirement 7.1 | 5 | Disclosure and publication of information on the mining sector in an easily understood language, preparation of social advertising | Information sheets, infograms, EITI report, MSG annual report, information video-clips | MSG, RA Government Staff/ARM-EITI Secretariat | Ongoing | 45000 | World Bank, other donors, State budget | 15900 | State budget | ongoing | The cost of this line refers to the preparation and broadcasting of the TV programs covering the EITI implementation within the framework of the “Hraparakum” Governmental Television Program. In addition, the actual cost of several activities is presented in the activity N9. Namely, in 2017, two information leaflets on EITI implementation and USAID Armenia’s supported Project “Enhanced Transparency in the Mining Sector” have been prepared and published in Armenian and English. Five public service announcement (PSA) short videos and one short film have been filmed and published with support of the USAID Armenia, and regional visits and Armenia’s EITI candidacy event were organized.
|  |  | 6 | Awareness campaign on mining sector and EITI and their elucidation via social media (YouTube, Twitter, Facebook, etc.) | Information about mining and EITI published in social media | MSG, RA Government Staff/ARM-EITI Secretariat | Ongoing |  |  |  |  | ongoing | In 2017, the EITI Armenian Secretariat has been updating the implementation of Armenia's EITI on Facebook, YouTube and Twitter.
|  |  | 7 | Development of communication strategy | Draft communication strategy | MSG, RA Government Staff/ARM-EITI Secretariat, expert | 2017-05-01 | 2000 | Donors | 54000 | The British Embassy in Yerevan | delayed / ongoing | Within the scope of the project implemented with the support of the British Embassy in Yerevan, the development of the Communication Strategy was delegated to the AUA Center for Responsible Mining (AUA CRM). The works were implemented with delay from the deadline set out in the ToR. As of February 2018 the first draft of the Communication Strategy was presented by the AUA CRM. The 7th, 16th, 20th, 50th and 51th activities have also been funded by this Project.
|  |  | 8 | Approval of communication strategy | Communication strategy | MSG | 2017-06-01 |  |  |  |  | delayed | see activity N7
|  | requirement 7.1 | 9 | Implementation of awareness raising measures | Round tables, meetings, including with representatives of affected communities, meetings with educational institutions | MSG, RA Government Staff/ARM-EITI Secretariat | Ongoing | 10000 | World Bank, other donors, partners, State budget | 22000 | USAID Armenia, State budget | ongoing
|  | requirement 7.1 | 10 | Official presentation of EITI report / conference | EITI conference | MSG, RA Government Staff/ARM-EITI Secretariat, EITI Int. Secretariat | 2018-10-01 | 15000 | World Bank, other donors, partners, State budget
Development of roadmap for disclosure of ultimate beneficial owners | Reducing corruption risks, improving the investment environment and accountability | requirement 2.5
|  |  | 11 | Development of roadmap for disclosure of ultimate beneficiary owners | Draft roadmap | MSG, RA Government Staff/ARM-EITI Secretariat, RA government agencies | 2017-06-01 | 7000 | Donors, State budget | 23800 | EBRD | completed | The Roadmap of Beneficial Ownership Disclosure was developed by the EBRD financed experts in November-December, 2017. The MSG approved the Roadmap in December, 2017. The Armenia’s BO Disclosure Roadmap was published on January 1st, 2018, as it had been set forth in the EITI Board decision.
|  |  | 12 | Public consultations on the draft roadmap | Disclosure of the draft roadmap, meetings | MSG, RA Government Staff/ARM-EITI Secretariat | 2017-07-01 | 1000 | Donors, partners, State Budget |  |  | ongoing | see activity N11 The EBRD experts had held discussions not only with the members of the MSG, but also with other stakeholders and competent government agencies, NGOs and business community.
|  |  | 13 | Approval of the roadmap for disclosure of ultimate beneficiary owners | Roadmap | MSG | 2017-08-01 |  |  |  |  | completed | see activity N11
|  |  | 14 | Submission of the roadmap for disclosure of ultimate beneficiary owners to the EITI Secretariat | Roadmap submitted to the EITI Secretariat | RA Government Staff/ARM-EITI Secretariat | 2017-09-01 |  |  |  |  | completed | see activity N11
Review of the legal framework of Armenia, disclosure of inconsistencies and gaps with EITI Standard | Alignment of the Armenian legal framework for the purpose of implementing the EITI standard | requirement 2
|  |  | 15 | Preparation of the terms of reference by the MSG based on which local and international consultants will conduct a review for identifying inconsistencies | Terms of reference | MSG, RA Government Staff/ARM-EITI Secretariat | 2017-04-01 | 1000 | State Budget |  |  | completed | The ToR for the Legal Study has been developed and approved by the MSG in June-July, 2017.
|  |  | 16 | Review of legislation, identification of gaps, submission of recommendations on addressing the gaps | Report, action plan | MSG, RA Government Staff/ARM-EITI Secretariat, expert | 2017-12-01 | 15000 | donors | see activity N7 | The British Embassy in Yerevan | partially completed | The AUA CRM had submitted the package of draft Laws in November 2017, which was discussed with the stakeholder bodies and the MSG. The package of RA draft Laws was submitted to the Government of RA in December, 2017 and was approved by the Government on 18 January, 2018. 18. The package of RA draft Laws was submitted to the RA National Assembly. The AUA CRM has not yet submitted the Legal Study Report.
|  |  | 17 | Submission of the report and action plan to the MSG |  | RA Government Staff/ARM-EITI Secretariat, expert | 2017-12-01 |  |  |  |  | delayed | see activity N16
|  |  | 18 | Review and approval of report and action plan by the MSG | Report, action plan | MSG, RA Government Staff | 2017-12-01 |  |  |  |  | delayed | see activity N16
Review of the best international practices and development of roadmap for harmonization with the EITI and best responsible mining international experience | Implementation of responsible mining behavior | requirement 8.3.a.iii.
|  |  | 19 | Development and approval of the terms of reference | Terms of reference | MSG, RA Government Staff/ARM-EITI Secretariat | 2017-10-01 | 1000 | State budget |  | State budget | completed | The ToR for the Legal Study has been developed and approved by the MSG in June-July, 2017.
|  |  | 20 | Development of roadmap for reviewing international experience | Roadmap | MSG, RA Government Staff/ARM-EITI Secretariat | 2017-11-01 | 5000 | Donors | see activity N7 | The British Embassy in Yerevan | ongoing | According to the ToR for the Legal Study, the Roadmap is part of the Legal Study Report. see activity N16
|  |  | 21 | Approval of the roadmap by the MSG | Action plan, budget | MSG | 2018-01-01 |  |  |  |  | delayed | see activities N16 and N20
|  |  | 22 | Implementation of action plan |  | MSG, RA Government Staff/ARM-EITI Secretariat, RA government agencies | 2018-12-01 | 50000 | World Bank, other donors, partners |  |  | delayed | see activities N16 and N20
|  |  | 23 | Involvement in development of the sector policy | Involvement, provision of feedback | MSG, RA Government Staff/ARM-EITI Secretariat | Ongoing |  |  |  |  | ongoing
Ensuring Armenia's EITI candidacy status | Implementation of the EITI standard
|  | requirement 1.1 | 24 | RA Prime Minister's statement | Statement |  | 2015-07-01
|  | requirement 1.4.b. ii. | 25 | EITI awareness raising events | Meetings |  | 2015-12-01
|  | requirement 1.2 requirement 1.3 | 26 | Nomination of MSG members | Nominated MSG members | MSG sub-groups | 2016-06-01
|  |  | 27 | Training seminars for MSG members | Training seminars | MSG, RA Government Staff, donors, experts | Mar-16 - Nov-16
|  | requirement 1.4.b | 28 | Development of the ToR of the MSG | draft ToR of the MSG | MSG, RA Government Staff | 2016-09-01
|  | requirement 1.4.b | 29 | Approval of the ToR of the MSG | ToR of the MSG | MSG | 2016-12-01
|  | requirement 1.4 | 30 | Participation in EITI Board meetings | EITI Board meetings | MSG, RA Government Staff
|  | requirement 1.4 | 31 | MSG meeting | MSG meeting | MSG, RA Government Staff | 27.06.2016
|  |  | 32 | First official meeting of MSG, launching event | Firts official meeting of MSG, launching event | MSG, RA Government Staff | 25.11.2016
|  | requirement 1.4.a. iii. | 33 | Adoption of RA Prime Minister Decree on Setting Up the RA EITI Multi-Stakeholder Group and Approving Its Composition | RA Prime Minister decree | RA Government Staff | 24.11.2016
|  | requirement 1.5 requirement 1.4.b.iv. | 34 | Development of Armenia's EITI work program | Armenia's draft EITI work program | MSG, RA Government Staff | 2016-12-01
|  | requirement 1.5 requirement 1.4.b.iv. | 35 | Approval of Armenia's EITI work program | Armenia's EITI work program | MSG | 2016-12-01
|  | requirement 1.4 | 36 | Development of the RA EITI candidature application | Draft RA EITI candidacy application | MSG, RA Government Staff | 2016-12-01
|  | requirement 1.4 | 37 | Approval of the RA EITI candidature application | RA EITI candidacy application | MSG | 2016-12-01
|  |  | 38 | Collaboration with donors | Meetings with donors | RA Government Staff | Ongoing |  |  |  |  | ongoing | As a result of the activities carried out by the Armenian EITI Secretariat, cooperation has been established with USAID Armenia, EBRD, and the British Embassy in Yerevan. A grant application has been prepared for WB support to EITI Armenia, and systematic works have been carried out with the diplomatic representatives in Armenia and overseas. Preliminary discussions were held with GIZ Armenia.
|  | requirement 1.4 | 39 | Submission of the RA EITI candidature application to the EITI international secretariat | Submitted RA EITI candidacy application | RA Government Staff | 2016-12-01
|  |  | 40 | Establishment and operation of the Armenian EITI secretariat | Armenian EITI secretariat | RA Government Staff | Oct - 2017- Dec - 2018 | 120000 | World Bank, State budget | 63900 | USAID Armenia, State budget | completed | In 2017 the functions of the national EITI Secretariat have been carried out by the experts of the Project “Enhanced Transparency in the Mining Sector” of the Government Staff of Armenia with the support of USAID Armenia. The EITI Secretariat of Armenia was established under the RA Government Staff in January 2018.
|  | requirement 1.4.b.iv. requirement 7.4 | 41 | Preparation and approval of the RA EITI MSG annual report | Annual report of the RA EITI MSG | MSG, RA Government Staff/ARM-EITI Secretariat | Jan - 2018 Jan - 2019 |  |  |  |  | ongoing | The annual EITI activity report for 2017 shall be prepared and published by July 1, 2018 as set out by the EITI Board.
|  | requirement 1.4.b.iv. requirement 7.4 | 42 | Preparation of monitoring reports on the RA EITI MSG activities, EITI implementation, action plan (quarterly, biannual, annual) | Reports | MSG, RA Government Staff/ARM-EITI Secretariat | Quarterly |  |  |  |  | completed | In 2017 the EITI implementation quarterly reports were developed and approved by the EITI MSG of Armenia.
|  | requirement 1.4 | 43 | Collaboration with the EITI international secretariat and other EITI member countries | Correspondence, meetings, conference calls | RA Government Staff/ARM-EITI Secretariat, MSG | Ongoing |  |  |  |  | ongoing
|  |  | 44 | Participation in EITI Board meetings and conferences |  | MSG, RA Government Staff/ARM-EITI Secretariat | Ongoing | 70000 | World Bank, other donors | 11500 | World Bank, USAID Armenia | completed | With the World Bank's funding, 2 MSG members took part in the EITI conference held in Bogota Colombia in 2017. And the USAID funding the head of the national EITI Secretariat participated BO Disclosure held in Jakarta. Participation of the MSG members form the extractive companies was self-financed.
|  | requirement 1.4 | 45 | Holding of the RA EITI MSG meetings | RA EITI MSG meetings | RA Government Staff/ARM-EITI Secretariat, MSG | Quarterly | 2000 | State budget |  |  | completed | In 2017 the EITI MSG of Armenia held 5 official meetings.
|  | requirement 1.5.f | 46 | Revision and approval of the EITI work plan | Revised EITI work plan | MSG, RA Government Staff/ARM-EITI Secretariat | Jan - 2018 Jan - 2019 |  |  |  |  | ongoing
|  |  | 47 | Creation of MSG working groups |  | MSG | Ongoing |  |  |  |  | ongoing | In 2017 the EITI MSG of Armenia formed five working groups.
|  |  | 48 | Development and approval of the 2019-2020 EITI work program | 2019-2020 EITI work program | MSG, RA Government Staff/ARM-EITI Secretariat | 2018-10-01
|  |  | 49 | Payment of EITI membership fee |  |  | Dec - 2017 Dec - 2018 | 20000 | State budget
Comprehensive report consistent with the EITI standard | Presentation of report under the EITI standard, publication of comprehensive information on the sector
|  |  | 50 | Scoping study of EITI report | scoping study | RA Government Staff/ARM-EITI Secretariat, MSG | 2017-06-01 | 1000 | State budget | see activity N7 | The British Embassy in Yerevan | ongoing | Within the scope of the project implemented with the support of the British Embassy in Yerevan, preparation of the EITI Scoping Study was commissioned to the AUA CRM. The works were implemented with delay from the deadline set out in the ToR. As of February 2018 the final draft of the EITI Scoping Study was submitted by the AUA CRM.
|  | requirement 1.4.b.iv. | 51 | Developing the ToR for the independent administrator | Draft ToR for the independent administrator | RA Government Staff/ARM-EITI Secretariat, MSG, RA government agencies | 2017-07-01 | 1000 | State budget | see activity N7 | The British Embassy in Yerevan | ongoing | Within the scope of the project implemented with the support of the British Embassy in Yerevan, preparation of the ToR for the Independent Administrator were commissioned to the AUA CRM. The works were implemented with delay from the set out deadline. As of February 2018 the draft of the ToR for the Independent Administrator was submitted by the AUA CRM.
|  | requirement 4.9. b.iii | 52 | Discussion and approval of the ToR for the independent administrator | ToR for the independent administrator | MSG, RA Government Staff/ARM-EITI Secretariat | 2017-08-01 |  |  |  |  | delayed | see activity N51
|  | requirement 1.4.b.iv. | 53 | Selection of the independent administrator (tender and approval) and preparation of the EITI report of Armenia | Tender announcement for independent administrator, tender, contract awarded to the independent administrator, EITI report of Armenia | RA Government Staff/ARM-EITI Secretariat, MSG, independent administrator | Oct-2017-July-2018 | 100000 | World bank |  | World Bank | delayed | The Independent Administrator's tender announcement will be possible to publish in the 2nd quarter of 2018, after the approval of the World Bank's Assistance Grant Program for EITI Armenia.
|  |  | 54 | Preparation and approval of the list of reporting government agencies and entities by the MSG, definition of materiality | List of reporting government agencies and entities | RA Government Staff/ARM-EITI Secretariat, MSG, RA government agencies | 2017-11-01 |  |  |  |  | ongoing | see activity N53
|  |  | 55 | Development and approval of the format and timing of presentation of reporting by government agencies and extractive entities for the EITI Report purposes | Reporting format | RA Government Staff/ARM-EITI Secretariat, MSG, RA government agencies | 2017-11-01 |  |  |  |  | ongoing | see activity N53
|  |  | 56 | Training for government agencies and extractive entities on presentation of reports for the EITI report purposes | Training | RA Government Staff/ARM-EITI Secretariat, MSG, RA government agencies | 2017-12-01 | 5000 | State budget |  |  | delayed
|  |  | 57 | Discussion with the government of the need for legal bases for reporting | Discussion | RA Government Staff, MSG | 2017-11-01 |  |  |  |  | ongoing | see activity N16
|  |  | 58 | Discussion and approval of the RA EITI report prepared by the independent administrator | RA EITI Report | MSG,RA Government Staff/ARM-EITI Secretariat | 2018-07-01
|  |  | 59 | Translation work |  |  | Ongoing | 10000 | World bank, other donors, State budget | 1250 | USAID Armenia, State budget | ongoing | In 2017 the EITI standard has been translated into Armenian. The Armenian EITI Secretariat carried out translation of other materials, guidelines and templates.
|  |  | 60 | Submission of the RA EITI Report to the EITI Secretariat and its publication | RA EITI Report | RA Government Staff/ARM-EITI Secretariat, MSG | 2018-08-01
|  | requirement 7.3 | 61 | Review of considerations of the EITI Secretariat concerning the RA EITI Report and preparation of report on these considerations | Report | RA Government Staff/ARM-EITI Secretariat, MSG | 2018-12-01
STATUS OF ACTIVITIES | [9 empty] | * The 1st, 12th, 15th, 19th and 43th activities were implemented by the EITI Secretariat of Armenia and the Government Staff.
Accomplished
Open | [9 empty] | NOTE: Currency exchange rates as of 12 January: 1 EUR = 1.19USD, 1 GBP =1.35USD 1USD = 480 AMD
Ongoing